## ERP project timelines
| Year | 2015-07-01 | [13 empty] | 2015-10-07 | [12 empty] | 2016-01-06 | [12 empty] | 2016-04-06 | [12 empty] | 2016-07-06 | [12 empty] | 2016-10-05 | [12 empty] | 2017-01-04 | [12 empty] | 2017-04-05
| Quarter | Q3 | [13 empty] | Q4 | [12 empty] | Q1 | [12 empty] | Q2 | [12 empty] | Q3 | [12 empty] | Q4 | [12 empty] | Q1 | [12 empty] | Q2
| Month | 2015-07-01 |  |  |  |  | 2015-08-05 |  |  |  | 2015-09-02 |  |  |  |  | 2015-10-07 |  |  |  | 2015-11-04 |  |  |  | 2015-12-02 |  |  |  |  | 2016-01-06 |  |  |  | 2016-02-03 |  |  |  | 2016-03-02 |  |  |  |  | 2016-04-06 |  |  |  | 2016-05-04 |  |  |  | 2016-06-01 |  |  |  |  | 2016-07-06 |  |  |  | 2016-08-03 |  |  |  |  | 2016-09-07 |  |  |  | 2016-10-05 |  |  |  | 2016-11-02 |  |  |  |  | 2016-12-07 |  |  |  | 2017-01-04 |  |  |  | 2017-02-01 |  |  |  | 2017-03-01 |  |  |  |  | 2017-04-05 |  |  |  | 2017-05-03 |  |  |  |  | 2017-06-07
Project Lead | Week Beginning | time axis 2015-06-29 to 2017-06-26
| Weds | 2015-07-01 | 2015-07-08 | 2015-07-15 | 2015-07-22 | 2015-07-29 | 2015-08-05 | 2015-08-12 | 2015-08-19 | 2015-08-26 | 2015-09-02 | 2015-09-09 | 2015-09-16 | 2015-09-23 | 2015-09-30 | 2015-10-07 | 2015-10-14 | 2015-10-21 | 2015-10-28 | 2015-11-04 | 2015-11-11 | 2015-11-18 | 2015-11-25 | 2015-12-02 | 2015-12-09 | 2015-12-16 | 2015-12-23 | 2015-12-30 | 2016-01-06 | 2016-01-13 | 2016-01-20 | 2016-01-27 | 2016-02-03 | 2016-02-10 | 2016-02-17 | 2016-02-24 | 2016-03-02 | 2016-03-09 | 2016-03-16 | 2016-03-23 | 2016-03-30 | 2016-04-06 | 2016-04-13 | 2016-04-20 | 2016-04-27 | 2016-05-04 | 2016-05-11 | 2016-05-18 | 2016-05-25 | 2016-06-01 | 2016-06-08 | 2016-06-15 | 2016-06-22 | 2016-06-29 | 2016-07-06 | 2016-07-13 | 2016-07-20 | 2016-07-27 | 2016-08-03 | 2016-08-10 | 2016-08-17 | 2016-08-24 | 2016-08-31 | 2016-09-07 | 2016-09-14 | 2016-09-21 | 2016-09-28 | 2016-10-05 | 2016-10-12 | 2016-10-19 | 2016-10-26 | 2016-11-02 | 2016-11-09 | 2016-11-16 | 2016-11-23 | 2016-11-30 | 2016-12-07 | 2016-12-14 | 2016-12-21 | 2016-12-28 | 2017-01-04 | 2017-01-11 | 2017-01-18 | 2017-01-25 | 2017-02-01 | 2017-02-08 | 2017-02-15 | 2017-02-22 | 2017-03-01 | 2017-03-08 | 2017-03-15 | 2017-03-22 | 2017-03-29 | 2017-04-05 | 2017-04-12 | 2017-04-19 | 2017-04-26 | 2017-05-03 | 2017-05-10 | 2017-05-17 | 2017-05-24 | 2017-05-31 | 2017-06-07 | 2017-06-14 | 2017-06-21 | 2017-06-28
| Month | 7 | 7 | 7 | 7 | 7 | 8 | 8 | 8 | 8 | 9 | 9 | 9 | 9 | 9 | 10 | 10 | 10 | 10 | 11 | 11 | 11 | 11 | 12 | 12 | 12 | 12 | 12 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 4 | 4 | 4 | 4 | 5 | 5 | 5 | 5 | 6 | 6 | 6 | 6 | 6 | 7 | 7 | 7 | 7 | 8 | 8 | 8 | 8 | 8 | 9 | 9 | 9 | 9 | 10 | 10 | 10 | 10 | 11 | 11 | 11 | 11 | 11 | 12 | 12 | 12 | 12 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 4 | 4 | 4 | 4 | 5 | 5 | 5 | 5 | 5 | 6 | 6 | 6 | 6
| Quarter | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
| Year | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17
Richard | CO2-EOR | 2015-07-06: Plen; 2015-07-27: StGrp; 2015-09-07: ConfPres; 2015-10-05: RepL
| Hydrogen | 2015-10-12: PostPlen; 2016-01-25: Report revision……; 2016-02-29: Member Review; 2016-03-21: RepL; 2016-08-08: Report approval; 2016-09-26: Pub; 2016-10-10: RepL
| Smart Energy | 2015-11-09: Revision…; 2016-04-18: RepL; 2016-09-05: Redrafting report; 2016-10-03: Report approval?; 2016-10-31: Pub
| Public Engagement | 2016-04-25: WShop
| Industrial Efficiency | 2016-05-16: RepL
| Heat | 2016-09-05: StGrp (scoping); 2016-10-10: PID
Mark | Horizon Scanning | 2015-07-20: StGrp
| Workshop and Survey | 2015-09-14: LitRev; 2015-09-21: LitRev; 2015-09-28: Cse; 2015-10-05: StGrp; 2015-10-12: Plen; 2015-11-02: LitRev; 2015-11-09: LitRev; 2015-11-23: WShop; 2015-11-30: WShop; 2016-01-11: Plen; 2016-02-15: Wshop; 2016-02-29: LitRev; 2016-03-07: LitRev; 2016-03-14: StGrp; 2016-09-12: Draft; 2016-09-19: StGrp; 2016-10-17: LitRev; 2016-10-24: LitRev; 2016-10-31: LitRev; 2016-11-07: LitRev; 2017-01-16: Plen
Future of Utilities
| Phase 1 - Scenario development | 2016-04-18: PID; 2016-04-25: LitRev; 2016-05-02: LitRev; 2016-05-09: LitRev; 2016-05-16: LitRev; 2016-06-13: WShop
| Phase 2 - Stress Testing / Interviews | 2016-09-05: StGrp; 2016-09-26: Draft; 2016-10-10: Plen; 2016-10-31: WShop; 2016-11-14: WShop; 2016-11-28: WShop; 2016-12-26: Draft
Simon | Community Energy | 2015-07-27: RepAgree; 2015-09-07: RepL; 2015-09-21: Follow-up meetings re. recommendations
| Buildings | 2016-04-04: Research to update report; 2016-08-01: Redrafting report; 2016-10-03: Pub; 2016-10-10: RepL
Transport
| Phase 1 | 2015-07-27: RepL; 2015-08-03: internal; 2016-04-18: RepL
| Phase 2 | 2015-07-06: Scope; 2015-09-14: Analysis; 2015-10-12: Plen; 2016-04-18: RepL; 2016-05-02: Follow-up ==>
| Heat | 2016-08-01: Launch event preparation; 2016-09-05: StGrp (scoping); 2016-10-10: PID & WShop
| New contracts | 2016-07-04: Contract extension; 2016-10-03: 2017-2019 member's consortium agreement & EIB-ERP contract
Andy | Flexibility | 2015-08-10: RepL; 2015-09-21: CCC meet; 2015-11-23: Wshp
| International Engagement | 2015-10-12: Plen; 2016-01-11: Draft; 2016-03-14: RepL
| CA Extension | 2016-02-01: Member; 2016-02-22: Interviews ……..; 2016-04-18: Plen; 2016-07-11: Plen; 2016-08-22: Mem choose to cont; 2016-09-12: Extnsion sent out; 2016-09-26: Signed Up; 2017-01-02: START
| New CA | 2016-07-11: Plen; 2016-10-17: Draft CA to Members; 2017-02-13: Final CA to Members; 2017-03-27: Signed Up | START
| EIB contract | 2016-07-11: Plen; 2017-01-02: START
Helen | IE Strategies: Offshore/ Storage | 2015-10-12: OSW Strat
| Storage (details TBA) | 2015-11-30: StGrp; 2016-01-11: PID; 2016-07-11: Plen?; 2017-01-02: Pub; 2017-01-16: Follow-up ==>
| Manage Comms Strategy | 2015-08-17: Draft1; 2015-09-21: Draft2; 2015-10-12: Plen
Lindsay (UKERC) | Stakeholder mapping | 2016-09-26: Draft
Website - ongoing
| Newsletter | 2016-05-02: Make monthly; 2016-06-06: Pub; 2016-07-11: Pub; 2016-09-05: Pub; 2016-10-03: Pub; 2016-10-31: Pub; 2016-12-05: Pub; 2017-01-02: Pub; 2017-01-30: Pub; 2017-02-27: Pub; 2017-04-03: Pub; 2017-05-01: Pub; 2017-06-05: Pub
| ERP Impact Brochure | 2016-07-11: Pub
Key
StGrp | Milestone - Steering Group | bar: 2015-06-29
Draft | Milestone - Draft Paper | bar: 2015-06-29
LitRev | Milestone - Lit Review | bar: 2015-06-29
Model | Milestone - Model Complete | bar: 2015-06-29
Strat | Milestone - Strategy in place | bar: 2015-06-29
WShop | Milestone - Internal Workshop | bar: 2015-06-29
Webnr | Deliverable - Webinar | bar: 2015-06-29
RepL | Deliverable - Report Launch | bar: 2015-06-29
Plen | Deliverable - Plenary Presentation | bar: 2015-06-29
PostPlen | Deliverable - Post Plenary workshop | bar: 2015-06-29
PID | Deliverable - Project Initiation Doc | bar: 2015-06-29
Pub | Deliverable - Publication | bar: 2015-06-29
Delivered | report published, workshop help etc | bar: 2015-06-29